## Tool Dev (hidden)
| Status (Updated by JXS) | Tool Development - Remaining Tasks
Kelly | Resolved | Tabs for LU1.1a and LU1.1b have now been combined. Please fix the function in Summary Table so that the status for LU1.1 is correctly determined, drawing the status info from the one sheet.
Josh | Resolved | We need Instruction Information for the T.1.1 metrics based on your conversation with SJVAPCD. Remoive yellow hilites when you are done. Also - the metrics in Cell L12 of Summary Table and Tab T.1.1 match up. Please resolve and make consistent according to how the reductions are calculated and what we are asking the City to track. Maybe we keep the 10% participation rate as an assumption and not a tracking metric, unless SJVAPCD will be able to provide some relevant data? JXS Response: Updated the Summary sheet to provide the City guidance about what the SJVAPCD will be doing and how to follow up with them. Removed yellow highlights. Consolidated the two metrics into one, so that they are not separated out into two metrics (there was redundancy...before it was "10% of 10% of the worker population...but it is more simple to remove the 'percent participation' metric and simply make it 1% worker participation. Updated this in the energy workbook too). Then fixed the metrics in Summary Table cell L12 so that it matches up with T.1.1.
Josh | unresolved | We should lock these sheets so that they can’t be edited, including all yellow cells so the values can’t be changed
Josh | Resolved | Update workbook links to refer to links within this workbook
Josh | Resolved | Please check assumption, line 15 in tab E.1.3 - Are we assuming that 100% of Post-2005 commercial square footage will be upgraded by 2020? Are we really saying that all contruction post-2005 will be of a higher standard that what existed under 2005 baseline conditions? If so we can remove the part that says "= 100% of Post-2005 commercial square footage to be upgraded by 2020 " JXS Response: Yes -- all post-2005 square footage (new development) is assumed to utilize the available rebates -- the idea is that the City promotes these heavily for new development that occurs.
Josh | Resolved | Is the note for line 47 of the "Common Factors" tab still relevant? Does it need to be resolved. We don't want to keep this note in the tool. JXS Response: Removed.

## Instructions
Instructions for Using the Hughson CAP Monitoring Tool
Color Key
= monitoring tool input
= monitoring tool output
= CAP information, assumption, input , or common factor (do not change)
Instructions
General
The nine Climate Action Plan (CAP) stategies including in this tracking tool represent 100% of the GHG emissions reductions needed to reach the City of Hughson target for 2020. Annually update the performance data for each Strategy (green tabs) with current data. Do not change any of the values in the yellow tabs. The blue cells in the Summay Table tab display the results, including the estimated GHG emissions reduction associated with each Strategy, and the total reductions acheived to date relative to the 2020 target.
Strategy Worksheets
1. At top of each strategy sheet, enter current date 2. For each Implementing Action, select Status from drop-down menu (Not started, In Process, or Complete) 3. Enter data into all input fields (green cells). Do not change the data or information in the yellow cells.
Summary Table
Use the Table of CAP Monitoring Strategies to view a status summary for all strategies being monitored, and to determine progress against the 2020 GHG emissions reduction target associated with these strategies.
Explanation of Metrics (and Suggestions on Their Use)
CAP Strategy | Metric
E.1.1 | Total square feet of new construction residential space from 2005 to 2020
Total square feet of new residential space built in the City between 2005 and 2020. Can be estimated from data collected in building permits.
E.1.2 | Existing Residential Square Feet Upgraded by 2020
The total community residential area (in square feet) that is upgraded with energy efficiency programs/opportunites. Relevant data (e.g., number of program recipients) may be available from TID and PG&E related to their energy efficiency programs. Square footage can be estimated by multiplying the number of residences that are significantly upgraded by the average square footage of each residence in the City.
E.1.3 | Existing Commercial Square Feet Upgraded by 2020
Estimate the total existing (pre-2005) community commercial area (in square feet) that is upgraded with energy efficiency programs/opportunites, based on data collected from building permits, adjusted with a factor that accounts for the commercial upgrades that occur without obtaining permits.
Post-2005 Commercial Square Feet Upgraded by 2020
Estimate total new (post-2005) community commercial area (in square feet) that is upgraded with energy efficiency programs/opportunites, based on data collected from building permits, adjusted with a factor accounting for the commercial upgrades that occur without obtaining permits.
E.1.5 | Industrial Square Feet Upgraded by 2020
Estimate the total community industrial area (in square feet) that newly complies with SJVAPCD Best Performance Standards, using data collected from SJVAPCD and building permits, adjusted with a factor accounting for industrial upgrades that occur without obtaining permits.
E.1.6 | Number of Housing Units participating in program by 2020
Number of Housing Units participating in Turlock Irrigation District’s Shade Tree Program by 2020.
Number of Commercial Units participating in program by 2020
Number of Commercial Units participating in Turlock Irrigation District’s Shade Tree Program by 2020.
Number of trees planted per year
Total number of trees planted since 2005.
E.2.1 | On-Site Renewable Energy for Homes
Number of residential solar system installed since 2005.
T.1.1 | % of Job-workers Participating (in 4-day work week)
% of Hughson community members involved in the San Joaquin Valley Air Pollution Control District's (SJVAPCD) Commute Reduction Program's 4-day work week. The SJVAPCD expects to conduct a survey of the success of its Commute Reduction Program in 2015. This survey will provide information on the the % participation rate by jurisdiction. The City of Hughson should follow-up with the SJVAPCD1 for the results, to find out the number of community members that have become involved.
Total Number of Program Participants in 2020
Total number of persons participating in the program (now carpooling). The SJVAPCD is tracking this in 2015 with the survey. See cell above for information on how to obtain results from the SJVAPCD.
LU.1.1 | % Increase in residential units/acre by 2020
% Increase in City residential units/acre by 2020 (within City limits only), tracked through the development review process.
Proportional increase in local jobs, by 2020
% Increase in City residential units/acre by 2020 (within City limits only).
SW.1.1 | % Reduction in Per Capita Community Waste Sent to Landfill in 2020
Calculate % Reduction in Per Capita Community Waste Sent to Landfill (relative to 2005), based on solid waste disposal information reported to the state under Title 14, California Code of Regulations (14 CCR).
W.1.1 | % Reduction in Water Consumption 2020, relative to 2005
Calculate % reduction in total Community water consumption (relative to 2005).

## Summary Table
2013-12-05 | = Date of last update
Summary of CAP Monitoring Strategies
Strategy # | Implementation Status | Strategy Name |  |  | Target GHG Reduction in 2020 (MT CO2e) | sector % 2020 | % of 2020 target | % of 2020 CAP reductions | Actual GHG Reductions (MT CO2e) | Monitoring Metric(s)
Energy Goal E.1: Increase Building and Equipment Efficiency Community-Wide
Strategy E.1.1 | Not Started | Expand Green Building and Energy Efficient Design for New Residential Development |  |  | 446 | 31.68% | 13.7% | 13.39% | 0 | * Proportion of new homes that are assumed to meet 15% above Title 24
Strategy E.1.2 | In Progress | Promote Residential Energy Energy Efficiency Rebates, Programs, and Benchmarking | Participate in Energy Upgrade Program and promote existing rebates (PG&E, State, Federal) | 3.2222 | 128 | 9.091% | 3.931% | 3.843% | 0 | * Existing Residential Square Feet Upgraded by 2020
Strategy E.1.3 | In Progress | Promote Commercial / Industrial Energy Efficiency Rebates, Programs, and Benchmarking | Promote PG&E commercial and industrial energy efficiency/demand response programs | 3.4444 | 543 | 38.57% | 16.68% | 16.3% | 0 | * Existing Commercial Square Feet Upgraded by 2020 * Post-2005 Commercial Square Feet Upgraded by 2020
Strategy E.1.5 | Not Started | Improve Industrial Equipment Energy Efficiency |  |  | 100 | 7.102% | 3.071% | 3.002% | 0 | * Commercial Square Feet Upgraded by 2020
Strategy E.1.6 | In Progress | Establish and Monitor Voluntary Shade Tree Program | Incentivize solar energy installation | 3.1444 | 242 | 17.19% | 7.432% | 7.265% | 0 | * Number of Housing Units participating in program by 2020 * Number of Commercial Units participating in program by 2020 * Number of trees planted per year
Strategy E.2.1 | Not Started | On-Site Renewable Energy for Homes | Implement program for shade trees | 2.8444 | 307 | 21.8% | 9.429% | 9.216% | 0 | * Number of New Solar PV Systems by 2020
Goal T1. Reduce Single-Occupancy Vehicle Travel
Strategy T.1.1 | Not Started | Implement Voluntary Local Commute Trip Reduction Program |  |  | 347 | 26.03% | 10.66% | 10.42% | 0 | * % of Job-workers Participating in 4-day work week * Total Number of Program Recipients in 2020 * Percent of Recipients Participating
Goal T5. Promote Sustainable Growth Patterns
Strategy LU.1.1 | Not Started | Encourage Higher Density and Mixed Use Growth Patterns |  |  | 759.7485 | 57% | 23.33% | 22.81% | 0 | * % Increase in residential units/acre by 2020 * % increase in local jobs, by 2020
Goal SW.1: Reduce Community Solid Waste Sent to Landfill
Strategy SW.1.1 | In Progress | Reduced Total Community Waste Tonnage Sent to Landfill by 20% |  |  | 86 | 89.58% | 2.641% | 2.582% | 0 | * % Reduction in Per Capita Community Waste Sent to Landfill in 2020, relative to 2005
Goal W.1: Increase Community Water Conservation
Strategy W.1.1 | Not Started | Reduce Community Water Consumption by 20%. |  |  | 88.6 | 100% | 2.721% | 2.66% | 0 | * % Reduction in Water Consumption 2020, relative to 2005
|  |  |  | TOTAL | 3047.3485 |  | 93.59% | 91.48% | 0
|  |  |  | Needed to reach target | 3256 |  |  | Estimate | 0% | of 2020 target achieved
|  | 10 CAP monitoring strategies by sector |  |  |  | All 25 CAP strategies by sector
|  | Sector | 2020 reduction estimate | % of target |  | Sector | 2020 est. | % of target | % of CAP
|  | Energy | 1766 | 54.24% |  | Energy | 1813 | 55.68% | 54.43%
|  | LU&T | 1106.7485 | 33.99% |  | LU&T | 1333 | 40.94% | 40.02%
|  | Waste | 86 | 2.641% |  | Waste | 96 | 2.948% | 2.882%
|  | Water | 88.6 | 2.721% |  | Water | 89 | 2.733% | 2.672%
|  | TOTAL | 3047.3485 | 93.59% |  | TOTAL | 3331 | 102.3% | 100%

## Common Factors
Common Factors
Factors with a pale yellow background color are not subject to change for Hughson. Factors with a pale green background color are subject to modification, based on the implementation depth of the particular reduction strategy.
Factor names with a blue background are subject to change for other jurisdictions (subject to modification per the Model CAP tool).
| # | Unit | Direct Data Source
Basic Unit Factors
Hours in a year | 8760
Hours of daylight in a year | 2920
Pounds per Metric Ton | 2204.62
Kwh per Mwh | 1000
lbs of CO2 emissions from 1 therm of natural gas | 11.7
GHG Emission Factors
TID Electricity emission factor (lbs/kWh) | 0.682 | lbs CO2/kWh | CCAR Reported 2006 Value for TID (Also used by ICF)
TID Emission Factor (MT/MWh) | 0.30935 | MT CO2/MWh
TID Electricity emission factor (lbs/MWh) | 0.029 | lbs CH4/MWh | EPA E-Grid Values for California (Also used by ICF)
TID Electricity emission factor (lbs/MWh) | 0.011 | lbs N2O/MWh | EPA E-Grid Values for California (Also used by ICF)
Natural Gas emission factor (kg/MMBtu) | 53.02 | kg CO2/MMBtu | LGOP, Table G.1, 'Pipeline (US Weighted average)'
Natural Gas emission factor (kg/MMBtu) | 0.005 | kg CH4/MMBTU | LGOP, Table G.3, 'Commercial' and 'Residential'
Natural Gas emission factor (kg/MMBtu) | 0.0001 | kg N2O/MMBTu | LGOP, Table G.3, 'Commercial' and 'Residential'
Projected City Growth Factors
Average Square Feet Per Residential Unit (Existing Housing Stock) | 1448 | square ft | See California Statewide Residential Appliance Saturation Study, page 10
Average Square Feet Per Residential Unit (New Housing Stock) | 2061 | square ft | See California Statewide Residential Appliance Saturation Study, page 10
2005 Residential Square Feet | 2772920 | square ft | Housing*Average Sq. Ft. Per Residential Unit
2020 Residential Square Feet | 4081655 | square ft | Housing*Average Sq. Ft. Per Residential Unit
2030 Residential Square Feet | 5009105 | square ft | Housing*Average Sq. Ft. Per Residential Unit
2005 Non-Residential Square Feet | 640500 | square ft | Source: GP EIR: 435,000 sf of industrial, 237,000 sf of commercial, and 360,000 sf of public uses.
2020 Non-Residential Square Feet | 640500 | square ft | Based on Employment Projections
2030 Non-Residential Square Feet | 769626.1682 | square ft | Based on Employment Projections
Total square feet of new construction residential space from 2005 to 2020 | 1308735 | square ft
Total square feet of new construction residential space from 2005 to 2030 | 2236185 | square ft
Total sq. feet of new construction commercial space from 2005 to 2020 | 64050 | square ft
Total sq. feet of new construction commercial space from 2005 to 2030 | 129126.1682 | square ft
Total # of housing units in the City in 2005 | 1915 | Housing Units | Source: ICF Inventory
Total # of housing units in the City in 2020 | 2550 | Housing Units | Source: StanCOG 'Un-adopted' Projections
Total # of housing units in the City in 2030 | 3000 | Housing Units | Source: StanCOG 'Un-adopted' Projections
Total # of commerical units in the City in 2005 | 242 | units | US Economis Census, Average of 2002 and 2007 totals
Total # of commercial units in 2020 | 242 | units
Total # of commercial units in 2030 | 290.7877 | units
City Square Mileage | 1.815 | sq. mile | Source: U.S. Census
City Sphere-of-Influence (SOI) Square Mileage | 1.9 | sq. mile | Hughson 2005 General Plan, page I-5
City of Hughson Acres in 2005 | 1161.6 | Acres
City of Hughson Acres in 2020 | 1161.6 | Acres
City of Hughson Acres in 2030 | 2377.6 | Acres | Assumes City expands to include Sphere of Influence by 2030
Housing Units per Acre in 2005 | 1.6486 | units per acre
Housing Units per Acre in 2020 | 2.1952 | units per acre
Housing Units per Acre in 2030 | 1.2618 | units per acre
California State Energy Intensity Factors
Avg. electric use intensity for res. buildings in kWh/sq ft. - California | 3.5 | kwh/square foot | RASS | http://websafe.kemainc.com/RASS2009/Default.aspx
Avg. natural gas usage intensity for res. buildings in therms/sq ft - California | 0.31 | therms/square feet | RASS | http://websafe.kemainc.com/RASS2009/Default.aspx
Avg. electric use intensity for comm. buildings in kWh/sq ft. - California | 13.63 | kwh/square foot | (2005 California Land Use Survey)
Avg. natural gas usage intensity for comm. buildings in therms/sq ft - California | 0.26 | therms/square feet | (2005 California Land Use Survey)
City of Hughson (Derived) Energy Intensity Factors
City electric use intensity factor for res. buildings in kWh/sq ft. | 2.5689 | kwh/square foot | Based on 2005 Residential Square Footage and Provided Electricity TID Data ("Domestic" class)
City natural gas intensity factor for res. buildings in therms/sq ft. | 0.29657 | therms/square feet | Based on 2005 Residential Square Footage and Provided Natural Gas Data ("Residential" class)
City electric use intensity factor for comm. buildings in kWh/sq ft. | 2.65 | kwh/square foot | Based on 2005 Non-Residential Square Footage and Provided Electricity TID Data (Non-Domestic classes, excluding municipal)
City natural gas use intensity factor for comm. buildings in therms/sq ft. | 1.8259 | therms/square feet | Based on 2005 Non-Residential Square Footage and Provided Natural Gas Data ("Commercial" class)
Transportation Factors
Elasticity of VMT with respect to density (from: Boarnet and Handy, 2010) | 0.07
Stanislaus County Annual Tons CO2/day (EMFAC 2011) for 2020 | 9072.42 | Tons CO2/day
Stanislaus County Annual VMT/day (EMFAC 2011) for 2020 | 14219793 | VMT/day
Emission Factor; Annual MT CO2 per VMT (EMFAC 2011) for 2020 | 0.00063801 | MT CO2/VMT
Total Annual VMT in 2005 | 49065800 | VMT/year | Source: Fehr & Peers |  | 2005 daily VMT provided by StanCOG model * 347
Total Annual VMT in 2020 | 59908448 | VMT/year | Based on population growth projections to estimate from data provided by Fehr & Peers |  | from Fehr & Peers March 2 revised VMT
Total Commute VMT in 2005 | 13591226.6 | VMT/year | Nationwide, 27.7% of all VMT are commute trips (USDOT, Summary of Travel Trends 2009, Table 24, p. 44) |  | Nationwide, 27.7% of all VMT are commute trips (USDOT, Summary of Travel Trends 2009, Table 24, p. 44)
Total Commute VMT in 2020 | 16594640.096 | VMT/year | Nationwide, 27.7% of all VMT are commute trips (USDOT, Summary of Travel Trends 2009, Table 24, p. 44) |  | Nationwide, 27.7% of all VMT are commute trips (USDOT, Summary of Travel Trends 2009, Table 24, p. 44)
Total Highway VMT in 2005 | 22889195.7 | VMT/year | In 2005, 46.65 percent of all VMT in Stanislaus was on state highways (Caltrans MVSTAFF05, Appendix B) |  | In 2005, 46.65 percent ofall VMT in Stanislaus was on state highways (Caltrans MVSTAFF05, Appendix B)
Total Highway VMT in 2020 | 27947290.992 | VMT/year | In 2005, 46.65 percent of all VMT in Stanislaus was on state highways (Caltrans MVSTAFF05, Appendix B) |  | But, county has other highways through it that don't run through Oakdale
Cost Factors
BLS U.S. Department of Labor: Average Stanislaus County Salary | 40768 | Salary | based on Bureau of Labor Statistics U.S. Department of Labor, County Employement and Wages (News Release). Released on March 28, 2012.
BLS U.S. Department of Labor: Average Stanislaus County Hourly Rate | 20.22 | Hourly Rate | based on Bureau of Labor Statistics U.S. Department of Labor, County Employement and Wages (News Release). Released on March 28, 2012.
Other
Renewable Portfolio Standard (RPS) Adjustment Factor | 0.88 |  | See Hughson Community Inventory Workbook
Implementation Tracker Statuses
Not Started
In Progress
Completed

## E 1.1
Strategy E 1.1 - Monitoring Worksheet
2013-09-01 | = lastest update
Strategy Name | Residential Green Building Standards
Emissions Category | Energy
Strategy Description | Residential Green Building Standards. Expand green building and energy efficient design for new residential development. CalGreen Tier 1 standards represent 15% improved energy efficiency over Title 24 standards.
Key Implementing Actions | Status | Target date | Implementing Action
| Not Started | 2014 | Action E-1.1a: Revise the City of Hughson Municipal Code to require implementation of CalGreen Tier 1 building code standards for all new residential development.
| Not Started | 2014 | Action E-1.1b: Expedite permits for developments that exceed Title 24 requirements by 15%.
Key Assumptions for Resource Savings and GHG Calculations
Description |  |  | # | Unit | Equation Variable | Notes:
Forecasted total square feet of new residential construction from 2005 to 2020 |  |  | 0 | square ft | NCa | 2020 CAP Target = 964,548 square feet of new construction residential space from 2005 to 2020
Forecasted total square feet of new residential construction from 2005 to 2030 |  |  | 0 | square ft | NCb | 2030 CAP Target = 1,500,408 square feet of new construction residential space from 2005 to 2030
% Natural Gas Savings expected from 2013 Title 24 Update |  |  | 15% | percent | Sa
% Electricity Savings expected from 2013 Title 24 Update |  |  | 15% | percent | Sb
Additional reduction in electricity and nat. gas usage for new buildings meeting 2013 Title 24 Tier 1 (15% above minimum requirement). |  |  | 12.75% | percent | R
Residential development during the 2005-2020 timeframe expected to be compliant with Title 24 Tier 1 (2013 update, effective 1/1/2014). |  |  | 100% | percent | P2020 | Assuming implementation of code in 2014. All housing is expected to be subject to the City's ordinance to attain Title 24 Tier 1.
Residential development during the 2005-2030 timeframe expected to be compliant with Title 24 Tier 1 (2013 update, effective 1/1/2014). |  |  | 100% | percent | P2030 | Assuming implementation of code in 2014. All housing is expected to be subject to the City's ordinance to attain Title 24 Tier 1.
2005 baseline Hughson electric use intensity factor for res. buildings in kWh/sq ft. |  |  | 2.5689 | kwh/square foot | E
2005 baseline Hughson natural gas intensity factor for res. buildings in therms/sq ft. |  |  | 0.29657 | therms/square feet | N
Electricity emission factor (MT CO2/MWh) |  |  | 0.30935 | Metric Tons/MWh | Efa
Natural Gas emission factor (kg CO2/MMBtu) |  |  | 53.02 | kg CO2/MMBtu | Efb
Renewable Portfolio Standard (RPS) Adjustment Factor |  |  | 0.88 |  | F
Renewable Portfolio Standard (RPS) Adjustment Factor |  |  | 0.88 |  | F
2See Impact Analysis: 2008 Update to the California Energy Efficiency Standards for Residential and Nonresidential Buildings http://www.energy.ca.gov/title24/2008standards/rulemaking/documents/2007-11-07_IMPACT_ANALYSIS.PDF
Data Sources for Resource Savings and GHG Calculations
CALGreen Guidance: www.hcd.ca.gov/CALGreen.html
Impact Analysis: 2008 Update to the California Energy Efficiency Standards for Residential and Nonresidential Buildings http://www.energy.ca.gov/title24/2008standards/rulemaking/documents/2007-11-07_IMPACT_ANALYSIS.PDF
Projection of GHG Emissions for California Utilities: http://www.pge.com/includes/docs/pdfs/mybusiness/energysavingsrebates/incentivesbyindustry/GHG_Emission_Factor_Guidance.pdf
Residential and commercial electric and natural gas rates. http://www.pge.com/about/news/topics/ratereduction.shtml
State of Indiana. Green Building cost estimates. https://bloomington.in.gov/green-building-costs
1. Resource Savings: | New Residential Green Building Development: Total Electricity Savings by 2020 (kWh) = Nca × (Sb + R) x P2020 x E x F Total Natural Gas Savings by 2020 (therms)= Nca × (Sa + R) x P2020 x N Total Electricity Savings by 2030 (kWh) = Ncb × (Sb + R) x P2030 x E x F Total Natural Gas Savings by 2030: (therms) = Ncb × (Sa + R) x P2030 x N
| Total electricity savings by 2020= |  | 0 | kwh
| Total natural gas savings by 2020= |  | 0 | therms
| Total electricity savings by 2030= |  | 0 | kwh
| Total natural gas savings by 2030= |  | 0 | therms
2. GHG Calculations: | Total Emissions Savings (MT)= (Se/1000×Efa)+(Sg/10 × Efb/1000)
| Se = | total electricity savings (kWh)
| Sg= | total natural gas savings (therms)
| 1000 | = conversion factor for kWh to MWh (electricity equation) or from kg to metric tons (natural gas equation)
| 10 | = conversion factor for therm to MMBtu
| Total GHG Emissions Savings by 2020= |  | 0 | metric tons CO2
| Total GHG Emissions Savings by 2030= |  | 0 | metric tons CO2
Key Assumptions for Cost Calculations
Description |  |  | # | Unit | Equation Variable
Average hourly rate for City employees |  |  | 20.22 | $
Average annual salary for City employees |  |  | 40768 | $
Annual FTE |  |  | 0.1
Upfront FTE |  |  | 0.5
Data Sources for Cost Calculations
3. Cost Calculations: | Total Annual Cost = (Upfront Cost / 8 Year Investment Period) + Annual Labor Cost
Total Cost by 2020=
6624.8

## E 1.2
Strategy E 1.2 - Monitoring Worksheet
2013-12-05 | = lastest update
Strategy Name | Residential Energy Efficiency Promotion
Emissions Category | Energy
Strategy Description | Residential Energy Efficiency Promotion. Promote various federal, State, local, and utility programs and other opportunities to improve the energy efficiency of residential homes.
Key Implementing Actions | Status | Target date | Implementing Action
| Not Started | 2014 | Action E-1.2a: Promote existing residential energy efficiency programs.
| Not Started | 2014 | Action E-1.2b: Promote rebates for residential fixtures and appliances and other utility programs to improve energy efficiency in residential homes.
| Not Started | 2014 | Action E-1.2c: Develop a low-cost local education campaign to promote residential energy efficiency improvements
| Not Started | 2014 | Action E-1.2d: Participate in a residential Property Assessed Clean Energy (PACE) Program.
| In Progress | 2014 | Action E-1.2e: Continue to participate in the San Joaquin Valley Clean Energy Partnership and the Northern Central Valley Energy Improvement Joint Powers Authority to apply for available Federal grant funding for residential energy efficiency projects.
Key Assumptions for Resource Savings and GHG Calculations
Description |  |  | # | Unit | Equation Variable | Notes:
Existing Residential Square Feet Upgraded since 2005 |  |  | 0 | square ft. | Rsf2020 | 2020 CAP Target = = 277,292 square feet = 10% of 2005 residential square footage by 2020
Target Percentage of Electricity Savings1 |  |  | 10% | % | E
Target Percentage of Natural Gas Energy Savings1 |  |  | 25% | % | N
Hughson electric use intensity factor for res. buildings in kWh/sq ft. |  |  | 2.5689 | kwh/square foot | Re
Hughson natural gas intensity factor for res. buildings in therms/sq ft. |  |  | 0.29657 | therms/square feet | Rn
Electricity emission factor (MT CO2/MWh) |  |  | 0.30935 | Metric Tons/MWh | Efa
Natural Gas emission factor (kg CO2/MMBtu) |  |  | 53.02 | kg CO2/MMBtu | Efb
Renewable Portfolio Standard (RPS) Adjustment Factor |  |  | 0.88 |  | F
1Based on NRDC estimates of the long-term, annual energy reduction impact of individual performance benchmarking
Data Sources for Resource Savings and GHG Calculations
2005 California End Use Survey http://www.energy.ca.gov/ceus/
RASS - California Statewide Residential Appliance Saturation Survey http://websafe.kemainc.com/RASS2009/Default.aspx
Natural Resource Defense Council. Propery Assessed Clean Energy Programs White Paper: http://pacenow.org/documents/PACE%20White%20Paper%20May%203%20update.pdf
1. Resource Savings: | Promote Residential Energy Efficiency: Residential Electricity Energy Savings (kWh)=E × Rsf2020 × Re x F Residential Natural Gas Savings (therms)=N × Rsf2020 × Rn
| Total residential electricity savings by 2020= |  | 0 | kwh/year
| Total residential natural gas savings by 2020= |  | 0 | therms/year
2. GHG Calculations: | Total Emissions Savings (MT)= (Se/1000×Efa)+(Sg/10 × Efb/1000)
| Se = | total electricity savings (kWh)
| Sg= | total natural gas savings (therms)
| 1000 | = conversion factor for kWh to MWh (electricity equation) or from kg to metric tons (natural gas equation)
| 10 | = conversion factor for therm to MMBtu
| Total GHG Emissions Savings by 2020= |  | 0 | metric tons CO2
Key Assumptions for Cost Calculations
Description |  |  | # | Unit | Equation Variable |  | 0
Average hourly rate for City employees |  |  | 20.22
Average annual salary for City employees |  |  | 40768
Annual FTE |  |  | 0.5
Data Sources for Cost Calculations
3. Cost Calculations: | Total Annual Cost = (Upfront Cost / 8 Year Investment Period) + Annual Labor Cost
Total Cost by 2020=
20384

## E 1.3
Strategy E.1.3 - Monitoring Worksheet
2013-12-05 | = lastest update
Strategy Name | Commercial Energy Efficiency Promotion
Emissions Category | Energy
Strategy Description | Promote various federal, State, local, and utility programs and other opportunities to improve the energy efficiency of commercial buildings.
Key Implementing Actions | Status | Target date | Implementing Action
| Not Started | 2014 | Action E-1.3a: Promote rebates for commercial fixtures and appliances and other utility programs to improve energy efficiency in commercial buildings.
| Not Started | 2014 | Action E-1.3b: Develop a local education campaign to promote benchmarking and cost-effective commercial energy efficiency improvements such as performing energy audits, use of building insulation and building envelope sealing, use of energy efficient appliances, and other efficiency programs that save energy.
| In Progress | 2014 | Action E-1.3c: Continue to participate in the San Joaquin Valley Clean Energy Partnership and the Northern Central Valley Energy Improvement Joint Powers Authority to apply for available Federal grant funding for non-residential energy efficiency projects.
Key Assumptions for Resource Savings and GHG Calculations
Description |  |  | # | Unit | Equation Variable | Notes:
Existing Commercial Square Feet Upgraded between 2005 and 2020 |  |  | 0 | square ft. | Csf2020 | 2020 CAP Target = 192,150 square feet = 30% of 2005 existing commercial square footage to be upgraded by 2020
Post-2005 Commercial Square Feet Upgraded between 2005 and 2020 |  |  | 0 | square ft. | Csg2020 | 2020 CAP Target = 64,050 square feet = 100% of Post-2005 commercial square footage to be upgraded by 2020
Target Percentage of Electricity Savings for Existing Businesses3 |  |  | 10% | % | E
Target Percentage of Natural Gas Energy Savings for Existing Businesses3 |  |  | 25% | % | N
Target Percentage of Electricity Savings for Post-2005 Businesses3 |  |  | 5% | % | G
Target Percentage of Natural Gas Energy Savings for Post-2005 Businesses3 |  |  | 10% | % | M
Hughson electric use intensity factor for comm. buildings in kWh/sq ft. |  |  | 2.65 | kwh/square foot | Ce
Hughson natural gas use intensity factor for comm. buildings in therms/sq ft. |  |  | 1.8259 | therms/square feet | Cn
Electricity emission factor (MT CO2/MWh) |  |  | 0.30935 | Metric Tons/MWh | Efa
Natural Gas emission factor (kg CO2/MMBtu) |  |  | 53.02 | kg CO2/MMBtu | Efb
Renewable Portfolio Standard (RPS) Adjustment Factor |  |  | 0.88 |  | F
Data Sources for Resource Savings and GHG Calculations
2005 California End Use Survey http://www.energy.ca.gov/ceus/
RASS - California Statewide Residential Appliance Saturation Survey http://websafe.kemainc.com/RASS2009/Default.aspx
Natural Resource Defense Council. Propery Assessed Clean Energy Programs White Paper: http://pacenow.org/documents/PACE%20White%20Paper%20May%203%20update.pdf
1. Resource Savings: | Promote Residential Energy Efficiency: Commercial Electricity Energy Savings (kWh)=(E × Csf × Ce)+(G x Csg x Ce) x F Commercial Natural Gas Savings (therms)= (N × Csf × Cn)+(M x Csg x Cn) x F
| Total commercial electricity savings by 2020= |  | 0 | kwh/year
| Total commercial natural gas savings by 2020= |  | 0 | therms /year
2. GHG Calculations: | Total Emissions Savings (MT)= (Se/1000×Efa)+(Sg/10 × Efb/1000)
| Se = | 4.1112e-283
| Sg= | total natural gas savings (therms)
| 1000 | = conversion factor for kWh to MWh (electricity equation) or from kg to metric tons (natural gas equation)
| 10 | = conversion factor for therm to MMBtu
| Total GHG Emissions Savings by 2020= |  | 0 | 1.1203e-288
Key Assumptions for Cost Calculations
Description |  |  | # | Unit | Equation Variable
Average hourly rate for City employees |  |  | 20.22
Average annual salary for City employees |  |  | 40768
Annual FTE |  |  | 0.3
Data Sources for Cost Calculations
3. Cost Calculations: | Total Annual Cost = (Upfront Cost / 8 Year Investment Period) + Annual Labor Cost
Total Cost by 2020=
12230.4

## E 1.5
Strategy E 1.5 - Monitoring Worksheet
2013-12-05 | = lastest update
Strategy Name | Industrial Equipment Energy Efficiency Promotion
Emissions Category | Energy
Strategy Description | Promote San Joaquin Valley Air Pollution Control District Best Performance Standards to increase energy efficiency in industrial equipment.
Key Implementing Actions | Status | Target date | Implementing Action
| Not Started | 2014 | Action E-1.5a: Make information available regarding the San Joaquin Valley Air Pollution Control District Best Performance Standards for industrial energy efficiency.
Key Assumptions for Resource Savings and GHG Calculations
Description |  |  | # | Unit | Equation Variable | Notes:
Industrial Square Feet Upgraded since 2005 |  |  | 0 | square ft. | Csf2020 | 2020 CAP Target= 192,150 square feet = 30% of City 2005 non-residential square footage upgraded by 2020
Electricity Energy Savings |  |  | 5% | % | E | CAP assumption = 5% electricity savings for upgraded area
Natural Gas Energy Savings |  |  | 5% | % | N | CAP assumption = 5% natural gas savings for upgraded area
Hughson electric use intensity factor for comm. buildings in kWh/sq ft. |  |  | 2.65 | kwh/square foot | Ce
Hughson natural gas use intensity factor for comm. buildings in therms/sq ft. |  |  | 1.8259 | therms/square feet | Cn
Electricity emission factor (MT CO2/MWh) |  |  | 0.30935 | Metric Tons/MWh | Efa
Natural Gas emission factor (kg CO2/MMBtu) |  |  | 53.02 | kg CO2/MMBtu | Efb
Renewable Portfolio Standard (RPS) Adjustment Factor |  |  | 0.88 |  | F
Data Sources for Resource Savings and GHG Calculations
2005 California End Use Survey http://www.energy.ca.gov/ceus/
RASS - California Statewide Residential Appliance Saturation Survey http://websafe.kemainc.com/RASS2009/Default.aspx
1. Resource Savings: | Improve Industrial Equipment Energy Efficiency: Commercial Electricity Energy Savings (kWh)=E × Csf2020 × Ce x F Commercial Natural Gas Savings (therms)=N × Csf2020 × Cn Commercial Electricity Energy Savings (kWh)=E × Csf2030 × Ce x F Commercial Natural Gas Savings (therms)=N × Csf2030 × Cn
| Total commercial electricity savings by 2020= |  | 0 | kwh/year
| Total commercial natural gas savings by 2020= |  | 0 | therms /year
2. GHG Calculations: | Total Emissions Savings (MT)= (Se/1000×Efa)+(Sg/10 × Efb/1000)
| Se = | total electricity savings (kWh)
| Sg = | total natural gas savings (therms)
| 1000 | = conversion factor for kWh to MWh (electricity equation) or from kg to metric tons (natural gas equation)
| 10 | = conversion factor for therm to MMBtu
| Total GHG Emissions Savings by 2020= |  | 0 | metric tons CO2

## E 1.6
Strategy E 1.6 - Monitoring Worksheet
2013-12-05 | = lastest update
Strategy Name | Shade Trees
Emissions Category | Energy
Strategy Description | Increase shade trees in Hughson to cool buildings and pavement in the summer, which decreases energy use and reduces the “heat island effect” within the City.
Key Implementing Actions | Status | Target date | Implementing Action
| In Progress | 2014 | Action E-1.6a: Continue to support and promote Turlock Irrigation District’s Shade Tree Program by providing brochures on the specifics of the program and including information on the City’s website.
| Not Started | 2014 | Action E-1.6b: Complete preparation of and adopt an Urban Forest Plan to manage the urban forest in the City by maintaining and preserving existing trees and planting additional ones.
| In Progress | 2014 | Action E-1.6c: Continue to implement City Codes and ordinances that require planting of new trees, protection of existing trees, and replacement of trees that are removed.
| In Progress | 2014 | Action E-1.6d: Continue to implement landscaping requirements for commercial uses that require planting of new trees and other vegetation (i.e., shrubs, groundcover) of certain size.
Key Assumptions for Resource Savings and GHG Calculations
Description |  |  | # | Unit | Equation Variable | Notes:
Projected Residential Electricity Use in 2020 |  |  | 10485352.949 | kwh/year | Re2020
Projected Residential Natural Gas Use in 2020 |  |  | 1210506.8973 | therms/year | Rg2020
Number of Housing Units in 2020 |  |  | 2550 | housing units | H2020
Number of Housing Units participating in program |  |  | 0 | housing units | Hp2020 | 2020 CAP Target = 51 = 2% of housing units participating in the City Shade Tree Program by 2020.
Projected Commercial Electricity Use in 2020 |  |  | 1697325 | kwh/year | Ce2020
Projected Commercial Natural Gas Use in 2020 |  |  | 1169470 | therms/year | Cg2020
Number of Commercial Units in 2020 |  |  | 242 | comm. units | C2020
Number of Commercial Units participating in program2 |  |  | 0 | comm. units | Cp2020 | 2020 CAP Target = 2.4 = 1% of commercial units participating in the City Shade Tree Program by 2020.
5% Reduction in energy use for residences (based on SMUD Calculator) |  |  | 95% |  | 0.95
Electricity emission factor (MT CO2/MWh) |  |  | 0.30935 | Metric Tons/MWh | Efa
Natural Gas emission factor (kg CO2/MMBtu) |  |  | 53.02 | kg CO2/MMBtu | Efb
# of trees planted since 2005 |  |  | 0 | trees | T | CAP target =2,820 trees planted by year 2020 ( 188 trees per year)
Renewable Portfolio Standard (RPS) Adjustment Factor |  |  | 0.88 |  | F
Data Sources for Resource Savings and GHG Calculations
SMUD Shade Tree Benefit Calculator https://usage.smud.org/treebenefit/iDefault.aspx "The simulations predicted annual total energy savings of about 3–5% from combined direct and indirect effects for old and new gas-heated single-family and rowhouse residences. This number increased to 10% for offices (SIC) and 12% for retail stores (sic)"
LBNL 2001 - Shade trees reduce building energy use and CO2 emissions from power plants "We estimate that a tree planted in Los Angeles avoids the combustion of 18 kg of carbon per tree annually"
EPA http://www.epa.gov/heatisland/resources/pdf/toronto_energysavings.pdf
1. Resource Savings: | Voluntary Shade Tree Program: Electricity savings residential by 2020 = Re2020/H2020 x HP2020 x 0.95 x F Natural gas savings residential by 2020 = Rg2020/H2020 x HP2020 x 0.95
| Total residential electricity savings by 2020= |  | 0 | kwh/year |  | Total City electricity savings by 2020= | 0 | kwh/year
| Total residential natural gas savings by 2020= |  | 0 | therms/year |  | Total City natural gas savings by 2020= | 0 | therms/year
| Total commercial electricity savings by 2020= |  | 0 | kwh/year
| Total commercial natural gas savings by 2020= |  | 0 | therms/year
2. GHG Calculations: | Total Emissions Savings (MT)= (Se/1000×Efa)+(Sg/10 × Efb/1000) + (T/0.001)
| Se = | total electricity savings (kWh)
| Sg= | total natural gas savings (therms)
| 1000 | = conversion factor for kWh to MWh (electricity equation) or from kg to metric tons (natural gas equation)
| 10 | = conversion factor for therm to MMBtu
| 0.001 | = conversion factor from kg to metric tons
| T | = number of trees planted since 2005
| Total GHG Emissions Savings by 2020 = |  | 0 | metric tons CO2
Key Assumptions for Cost Calculations
Description |  |  | # | Unit | Equation Variable
Average hourly rate for City employees |  |  | 20.22
Average annual salary for City employees |  |  | 40768
Annual FTE |  |  | 0.1
Upfront FTE |  |  | 0.25
Data Sources for Cost Calculations
3. Cost Calculations: | Total Annual Cost = (Upfront Cost / 8 Year Investment Period) + Annual Labor Cost
Total Cost by 2020=
5350.8

## E 2.1
Strategy E 2.1 - Monitoring Worksheet
2013-12-05 | = lastest update
Strategy Name | On-Site Renewable Energy for Homes
Emissions Category | Energy
Strategy Description | Increase on-site renewable energy generation and use in homes.
Key Implementing Actions | Status | Target date | Implementing Action
| Not Started | 2015 | Action E‐2.1a: Implement local ordinances and expedited permitting processes to support renewable energy in new residential uses.
| Not Started | 2015 | Action E‐2.1b: Participate in a commercial Property Assessed Clean Energy (PACE) Program.
| Not Started | 2015 | Action E‐2.1c: Strive to promote existing financial incentives for renewable energy system installations.
1California Solar Initiative Average Solar Installation Size: http://www.pge.com/includes/docs/pdfs/myhome/saveenergymoney/solarenergy/solar_consumer_guide.pdf (pg. 8)
2Assumed 10% of homes
3Assumed 20% of homes
Key Assumptions for Resource Savings and GHG Calculations
Description |  |  | # | Unit | Equation Variable | Notes:
Average solar installation size1 |  |  | 4 | kW | P
Number of New Solar PV Systems by 20202 |  |  | 0 | systems | S2020 | CAP target = 255= 10% of City’s homes install solar system by 2020; average capacity = 4 kW.
Hours of daylight in a year (assume six hours of sunlight per day) |  |  | 1380 | hrs/yr | H
Performance Ratio |  |  | 80% |  | R
Electricity emission factor (MT CO2/MWh) |  |  | 0.31 | Metric Tons/MWh | Efa
Renewable Portfolio Standard (RPS) Adjustment Factor |  |  | 0.88 |  | F
Data Sources for Resource Savings and GHG Calculations
Residential and commercial electric and natural gas rates. http://www.pge.com/about/news/topics/ratereduction.shtml
Solar capacity factor. http://en.wikipedia.org/wiki/Solar_power_in_California
1. Resource Savings: | Promote Small-scale On-site Renewable Energy for Homes: Energy Savings (kWh): P x S x H x R x F
| Total electricity savings by 2020= |  | 0 | kwh/year
2. GHG Calculations: | Total Emissions Savings (MT)= (Se/1000×Efa)+(Sg/10 × Efb/1000) + (T/0.001)
| Se = | total electricity savings (kWh)
| Sg= | total natural gas savings (therms)
| 1000 | = conversion factor for kWh to MWh (electricity equation) or from kg to metric tons (natural gas equation)
| 10 | = conversion factor for therm to MMBtu
| 0.001 | = conversion factor from kg to metric tons
| T | = number of trees planted since 2005
| Total GHG Emissions Savings by 2020 = |  | #REF! | metric tons CO2
Key Assumptions for Cost Calculations
Description |  |  | # | Unit | Equation Variable
Average hourly rate for City employees |  |  | 20.22
Average annual salary for City employees |  |  | 40768
Annual FTE |  |  | 0.1
Upfront FTE |  |  | 0.25
2. GHG Calculations: | Total Emissions Savings (MT)= (Se/1000×Efa)
| Se = | total electricity savings (kWh)
| 1000 | = conversion factor for kWh to MWh (electricity equation) or from kg to metric tons (natural gas equation)
| Total GHG Emissions Savings by 2020= |  | 0 | metric tons CO2

## T1.1
Strategy T.1.1 - Monitoring Worksheet
2013-12-05 | = lastest update
Strategy Name | Implement Voluntary Commute Trip Reduction Program
Emissions Category | Transportation and Land Use
Strategy Description | Support local employer-based trip reduction programs consistent with the San Joaquin Valley Air Pollution Control District’s Employer Based Trip Reduction Program (Rule 9410) to reduce the number of daily commuter vehicles to and from the City of Hughson. More information on eTRIP at: http://www.valleyair.org/Programs/Rule9410TripReduction/eTRIP_main.htm#what_is_rule
Key Implementing Actions | Status | Target date | Implementing Action
| Not Started | 2014 | Action T-1.1a: Promote SJVAPCD’s Employer Trip Reduction Implementation Program Rule 9410 (eTRIP), which requires larger employers to establish a program that encourages employees to reduce single-occupancy vehicle trips.
| Not Started | 2014 | Action T-1.1b: Encourage smaller employers to implement transportation demand management measures to reduce single-occupancy vehicle trips.
Key Assumptions for Resource Savings and GHG Calculations
Description |  |  | # | Unit | Equation Variable | Notes:
I. Telecommuting
Expected % of Job-workers Participating 1 |  |  | Use Telecommuting table below | % |  | 2020 CAP Target = 2% of local employees participating in a 4-day/40-hr workweek by 2020.
Work Week Choice |  |  | Use Telecommuting table below |  |  | Choose between 4-day/40 hr , 9-day/80 hr, and 1.5 days/week telecommuting
Emission Factor; Annual MT CO2 per VMT (EMFAC 2011) for 2020 |  |  | 0.00063801 | MT CO2/VMT | Cef2020
Commute VMT in 2020 |  |  | 16594640.096 | VMT/year | V2020
II. Carpool Program
Total Number of Program Participants in 2020 |  |  | 0 |  | R | CAP Target = 1% of City population (as of 2005) participating by 2020 (~74)
Average Daily Commute VMT per Person2 |  |  | 36.1333 |  | D
Working Days Per Year |  |  | 260 |  | W
Average Vehicle Occupancy in Carpool Vehicles |  |  | 2.5 |  | A
1 Based on a 10% particpation goal of eTrip, and 60% of all employees are at companies subject to eTrip and City requirements; SJVAPCD Final Staff Report, Rule 9140 (Employer Based Trip Reduction) December 17, 2009.
2Based on the 2011 Average Stanislaus County One-way Commute time to work of 27.1 minutes (See: http://www.dot.ca.gov/hq/tpp//offices/eab/socio_economic_files/2011/Stanislaus.pdf). Also assumes an average of 40 mph for the length of the commute.
Data Sources for Resource Savings and GHG Calculations
CAPCOA Quantifying Greenhouse Gas Mitigation Measures (Measure TRT-6). Note: Measure calculations based on data in Fehr & Peers, Moving Cooler Technical Appendices.
EMFAC 2011 model run, Mendocino County.
SJVAPCD Final Staff Report, Rule 9140 (Employer Based Trip Reduction) December 17, 2009.
SEEC Community Inventory Tool, Reduction Measure: Transportation - Carpooling. Available at: https://c.na5.visual.force.com/apex/ForecastMeasure
1. Resource Savings:
I: Telecommuting
VMT Reduction = VMT x % Reduction in Commute VMT See table below (Source: CAPCOA, TRT-6)
Employee Participation (% of local emplyees)
|  | 0% | 1% | 2% | 3% | 4% | 5% | 7.5% | 10% | 15% | 20% | 25%
% Reduction in Commute VMT
Work week | 9-day/80 hr | 0% | 0.07% | 0.14% | 0.21% | 0.28% | 0.35% | 0.525% | 0.7% | 1.05% | 1.4% | 1.75%
| 4-day/40 hr | 0% | 0.15% | 0.3% | 0.45% | 0.6% | 0.75% | 1.125% | 1.5% | 2.25% | 3% | 3.75%
| telecommuting 1.5 days | 0% | 0.22% | 0.44% | 0.66% | 0.88% | 1.1% | 1.65% | 2.2% | 3.3% | 4.4% | 5.5%
| % Reduction |  | 0% | Instruction: Use the table above to select value for % Reduction in Commute VMT, based on Work Week type and Employee Participation percentage. If there is participation in more than one type of work week, determine the % Reduction in Commute VMT for each work week type and add them together. Enter value in the cell to the left.
| VMT Reduction by 2020= |  | 0 | VMT
II: Carpool
Commute: VMT Reduction = R x P x D x W x A (Source: SEEC Reduction Measure Tool)
VMT Reduction by 2020= |  | 0 | VMT
2. GHG Calculations: | Total Emissions Savings (MT)= VMT Reduction x Cef
| Total GHG Emissions Savings by 2020= |  | 0 | metric tons CO2

## LU.1.1
Strategy LU.1.1 - Monitoring Worksheet
Note: This calculation calculates GHG emissions savings from increasing density. Density is expected to increase from 1.65 housing units per acre to 2.05 units/acre in 2020 and 2.28 units/acre in 2030. This will increase destination accessibility and otherwise reduce automobile dependency.
2013-12-05 | = lastest update
Strategy Name | Encourage Higher Density and Mixed Use Growth Patterns
Emissions Category | Transportation and Land Use
Strategy Description | Support higher densities, infill development, and sustainable growth patterns to reduce VMT.
Key Implementing Actions | Status | Target date | Implementing Action
| Not Started | 2014 | Action LU-1.1a: Implement the City’s Zoning Code that allows for higher densities, infill development, and mixed use that is pedestrian-friendly.
| Not Started | 2014 | Action LU-1.1b: Focus future development within the City limits and its Sphere of Influence to prevent urban sprawl and leapfrog development.
Key Assumptions for Resource Savings and GHG Calculations
Description |  |  | # | Unit | Equation Variable | Notes:
VMT in 2020 |  |  | 59908448 | VMT/year | V2020
% Increase in residential units/acre since 2005 |  |  | 0% | units/acre | A | CAP Target = 24.4% increase in units/acre by 2020 (congruent with General Plan expectations)
Elasticity of VMT with respect to density (from: Boarnet and Handy 2010) |  |  | 0.07 |  | EVMTd
Emission Factor; Annual MT CO2 per VMT (EMFAC 2011) for 2020 |  |  | 0.00063801 | MT CO2/VMT | Cef
Proportional increase in local jobs, since 20051 |  |  | 0% |  | Ia | CAP target = 1% increase in local jobs by 2020
Total Commute VMT in 2020 |  |  | 16594640.096 | VMT/year | Va
Data Sources for Resource Savings and GHG Calculations
CAPCOA Quantifying Greenhouse Gas Mitigation Measures (Measure LUT-1).
EMFAC 2011 model run, Stanislaus County.
Nelson\Nygaard, 2005. Crediting Low-Traffic Developments (p.12). Journal of the American Planning Association: http://www.montgomeryplanning.org/transportation/documents/TripGenerationAnalysisUsingURBEMIS.pdf
Boarnet, Marlon and Handy, Susan. 2010. "Draft Policy Brief on the Impacts of Residential Density Based on a Review of Empirical Literature."
Criteron Planner/Engineers and Fehr & Peers Associates (2001). Index 4D Method. A Quick-Response Method of Estimating Travel Impacts from Land-Use Changes. Technical Memorandum prepared for US EPA, October 2001.
1. Resource Savings: | Increase Density: VMT Reduction = VMT × (A × EVMTd)
| VMT Reduction by 2020= |  | 0 | VMT
Increase Local Employment Through Mixed Use Development: VMT Reduction = I x V
| VMT Reduction by 2020= |  | 0 | VMT
2. GHG Calculations: | Increase Density: Total Emissions Savings (MT)= VMT Reduction x Cef
| Total GHG Emissions Savings by 2020= |  | 0 | metric tons CO2
Increase Local Employment Through Mixed Use Development: Total Emissions Savings (MT)= VMT Reduction x Cef
| Total GHG Emissions Savings by 2020= |  | 0 | metric tons CO2

## SW.1.1
Strategy SW.1.1 - Monitoring Worksheet
2013-12-05 | = lastest update
Strategy Name | Reduce Total Community Waste Tonnage Sent to Landfill by 25%
Emissions Category | Solid Waste
Strategy Description | Reduce per capita community solid waste sent to landfill by 25% by 2020 and by 35% by 2030, compared with the baseline year 2005, through additional recycling, green waste diversion, and waste reduction associated with the community.
Key Implementing Actions | Status | Target date | Implementing Action
| Not Started | 2014 | Action SW-1.1a: Coordinate with Waste Management and Stanislaus County to prepare and distribute educational materials to the public on recycling programs, and to promote solid waste source reduction and benefits of composting.
| Not Started | 2014 | Action SW-1.1b: Work with Waste Management to expand the recycling program to include non-residential uses and multi-family residential uses.
| Not Started | 2014 | Action SW-1.1c: Work with Waste Management to explore expanding the recycling program to include food waste and green waste for all users.
| In Progress | 2014 | Action SW-1.1d: Continue to serve on and/or coordinate with the Stanislaus County Local Task Force on Solid Waste Management to ensure that services for solid waste collection, recycling, and disposal meet the needs of the community.
Key Assumptions for Resource Savings and GHG Calculations
Description |  |  | # | Unit | Equation Variable | Notes:
Total GHG Emissions (MT CO2e) of Community Waste Generation in 2020 |  |  | 344.4163 | MT CO2e | T2020
Projected Hughson Population in 2020 |  |  | 7437 | Population | P2020
MT CO2e Generated per Person (from Community Waste) in 2020 |  |  | 0.046311 | MT CO2e | M2020
Total GHG Emissions (MT CO2e) of Community Waste Generation in 2030 |  |  | 408.79 | MT CO2e | T2030 | Note: 408.79 (as of 03/06/2013)
Hughson Population in 2030 |  |  | 8287 | Population | P2030 | Projected to be 8,287
MT CO2e Generated per Person (from Community Waste) in 2030 |  |  | 0.049329 | MT CO2e | M2030
Percent Reduction in Per Capita Community Waste Sent to Landfill, relative to 2005 |  |  | 0% | % | Z2020 | CAP Target = 25% per capita reduction in community waste sent to landfill by 2020.
GHG Savings: | Reduce Total Community Waste Sent to Landfill: Total Solid Waste Savings (tons) = M x P x Z
| Total Solid Waste Savings by 2020 = |  | 0 | metric tons CO2

## Strategy E.1.X (hidden)
Strategy GHG and Cost Analysis Worksheet: E.1.X
Strategy Name | Update School Infrastructure for Greater Energy Efficiency
Emissions Category | Energy
Strategy Description | Pursue basic actions for school energy conservation. Assume other measures do not include schools.
Key Assumptions for Resource Savings and GHG Calculations
Description |  |  | # | Unit | Equation Variable
Commercial Square Feet Upgraded by 2020 |  |  | #REF! | square ft. | Csf2020 | Assumed 5% of 2005 non-residential square footage is affected by 2020
Commercial Square Feet Upgraded by 2030 |  |  | #REF! | square ft. | Csf2030 | Assumed 5% of 2005 non-residential square footage is affected by 2030
Target Percentage of Electricity Savings |  |  | 15% | % | E
Target Percentage of Natural Gas Energy Savings |  |  | 30% | % | N
Oakdale electric use intensity factor for comm. buildings in kWh/sq ft. |  |  | #REF! | kwh/square foot | Ce
Oakdale natural gas use intensity factor for comm. buildings in therms/sq ft. |  |  | #REF! | therms/square feet | Cn
Electricity emission factor (MT CO2/MWh) |  |  | #REF! | Metric Tons/MWh | Efa
Natural Gas emission factor (kg CO2/MMBtu) |  |  | #REF! | kg CO2/MMBtu | Efb
Data Sources for Resource Savings and GHG Calculations
2005 California End Use Survey http://www.energy.ca.gov/ceus/
RASS - California Statewide Residential Appliance Saturation Survey http://websafe.kemainc.com/RASS2009/Default.aspx
1. Resource Savings: | Commercial Electricity Energy Savings (kWh)=E × Csf2020 × Ce Commercial Natural Gas Savings (therms)=N × Csf2020 × Cn Commercial Electricity Energy Savings (kWh)=E × Csf2030 × Ce Commercial Natural Gas Savings (therms)=N × Csf2030 × Cn
| Total commercial electricity savings by 2020= |  | #REF! | kwh/year
| Total commercial natural gas savings by 2020= |  | #REF! | therms /year
| Total commercial electricity savings by 2030= |  | #REF! | kwh/year
| Total commercial natural gas savings by 2030= |  | #REF! | therms /year
2. GHG Calculations: | Total Emissions Savings (MT)= (Se/1000×Efa)+(Sg/10 × Efb/1000)
| Se = | total electricity savings (kWh)
| Sg= | total natural gas savings (therms)
| 1000 | = conversion factor for kWh to MWh (electricity equation) or from kg to metric tons (natural gas equation)
| 10 | = conversion factor for therm to MMBtu
| Total GHG Emissions Savings by 2020= |  | #REF! | metric tons CO2
| Total GHG Emissions Savings by 2030= |  | #REF! | metric tons CO2
Key Assumptions for Cost Calculations
Description |  |  | # | Unit | Equation Variable
Average hourly rate for City employees |  |  | #REF!
Average annual salary for City employees |  |  | #REF!
Annual FTE |  |  | 0.3
Data Sources for Cost Calculations
3. Cost Calculations: | Total Cost $= (Investment cost) - (cost savings)
| Total Cost by 2020= | #REF!
Total Cost by 2035=

## Strategy E.3.1 (hidden)
Strategy GHG and Cost Analysis Worksheet: E.3.1
Strategy Name | Pursue Funding to Establish City Revolving Loan Fund for Energy-Efficient Retrofits – Commercial Uses
Emissions Category | Energy
Strategy Description | Explore the establishment of revolving funds to finance energy-efficiency retrofits at businesses. Responsible Agency: Department of Community Development Next Steps: Conduct feasibility study of such a revolving fund. Develop guidelines for eligibility of recipients and energy measures. Discuss the possibililty with City Council members.
Key Assumptions for Resource Savings and GHG Calculations
Description |  |  | # | Unit | Equation Variable
Target for electricity savings |  |  | 0% | percent savings | Ee
Target for gas savings |  |  | 0% | percent savings | Eg
Commercial space upgraded by 2020 |  |  | #REF! | square feet | Csf2020 | Assumed 2% of 2005 non-residential square footage by 2020 (see Square Footage Calculations in Oakdale Buildout Table in Project Library)
Commercial space upgraded by 2030 |  |  | #REF! | square feet | Csf2030 | Assumed 4% of 2005 non-residential square footage by 2030
Oakdale electric use intensity factor for comm. buildings in kWh/sq ft. |  |  | #REF! | kwh/square foot | E
Oakdale natural gas use intensity factor for comm. buildings in therms/sq ft. |  |  | #REF! | therms/square feet | N
Electricity emission factor (MT CO2/MWh) |  |  | #REF! | Metric Tons/MWh | Efa
Natural Gas emission factor (kg CO2/MMBtu) |  |  | #REF! | kg CO2/MMBtu | Efb
Data Sources for Resource Savings and GHG Calculations
2005 California End Use Survey http://www.energy.ca.gov/ceus/
Projection of GHG Emissions for California Utilities - http://www.pge.com/includes/docs/pdfs/mybusiness/energysavingsrebates/incentivesbyindustry/GHG_Emission_Factor_Guidance.pdf
Residential and commercial electric and natural gas rates. http://www.pge.com/about/news/topics/ratereduction.shtml
1. Resource Savings: | Electricity Savings (kWh): Ee x (Csf2020 x E) Natural Gas Savings (therms) = Eg x (Csf2020 x N) Electricity Savings (kWh): Ee x (Csf2030 x E) Natural Gas Savings (therms) = Eg x (Csf2030 x N)
| Total electricity savings by 2020= |  | #REF! | kwh/year
| Total natural gas savings by 2020= |  | #REF! | therms/year
| Total commercial electricity savings by 2030= |  | #REF! | kwh/year
| Total natural gas savings by 2030= |  | #REF! | therms/year
2. GHG Calculations: | Total Emissions Savings (MT)= (Se/1000×Efa)+(Sg/10 × Efb/1000)
| Se = | total electricity savings (kWh)
| Sg= | total natural gas savings (therms)
| 1000 | = conversion factor for kWh to MWh (electricity equation) or from kg to metric tons (natural gas equation)
| 10 | = conversion factor for therm to MMBtu
| Total GHG Emissions Savings by 2020= |  | #REF! | metric tons CO2
| Total GHG Emissions Savings by 2030= |  | #REF! | metric tons CO2
Key Assumptions for Cost Calculations
Description |  |  | # | Unit | Equation Variable
Average hourly rate for City employees |  |  | #REF!
Average annual salary for City employees |  |  | #REF!
Up-front FTE |  |  | 0.25
Up-front Capital Cost |  |  | 10000
Data Sources for Cost Calculations
3. Cost Calculations: | Total Cost $= (Investment cost) - (cost savings)
| Total Cost by 2020= | #REF!
Total Cost by 2035=

## Strategy E.3.2 (hidden)
Strategy GHG and Cost Analysis Worksheet: E.3.2
Strategy Name | Pursue Funding to Establish City Revolving Loan Fund for Energy-Efficient Retrofits – Residential
Emissions Category | Energy
Strategy Description | Explore the establishment of revolving funds to finance energy-efficiency retrofits at businesses. Responsible Agency: Department of Community Development Next Steps: Conduct feasibility study of such a revolving fund. Develop guidelines for eligibility of recipients and energy measures. Discuss the possibililty with City Council members.
Key Assumptions for Resource Savings and GHG Calculations
Description |  |  | # | Unit | Equation Variable
Target for gas savings |  |  | 0% | percent savings | Ee
Target for gas savings |  |  | 0% | percent savings | Eg
Residential space upgraded by 2020 |  |  | #REF! | square feet | Csf2020 | Assumed 2% of 2005 non-residential square footage by 2020 (see Square Footage Calculations in Oakdale Buildout Table in Project Library)
Residential space upgraded by 2030 |  |  | #REF! | square feet | Csf2030 | Assumed 4% of 2005 non-residential square footage by 2030
Oakdale electric use intensity factor for res. buildings in kWh/sq ft. |  |  | #REF! | kwh/square foot | E
Oakdale natural gas intensity factor for res. buildings in therms/sq ft. |  |  | #REF! | therms/square feet | N
Electricity emission factor (MT CO2/MWh) |  |  | #REF! | Metric Tons/MWh | Efa
Natural Gas emission factor (kg CO2/MMBtu) |  |  | #REF! | kg CO2/MMBtu | Efb
Data Sources for Resource Savings and GHG Calculations
2005 California End Use Survey http://www.energy.ca.gov/ceus/
Projection of GHG Emissions for California Utilities - http://www.pge.com/includes/docs/pdfs/mybusiness/energysavingsrebates/incentivesbyindustry/GHG_Emission_Factor_Guidance.pdf
Residential and commercial electric and natural gas rates. http://www.pge.com/about/news/topics/ratereduction.shtml
1. Resource Savings: | Electricity Savings (kWh): Ee x (Csf2020 x E) Natural Gas Savings (therms) = Eg x (Csf2020 x N) Electricity Savings (kWh): Ee x (Csf2030 x E) Natural Gas Savings (therms) = Eg x (Csf2030 x N)
| Total electricity savings by 2020= |  | #REF! | kwh/year
| Total natural gas savings by 2020= |  | #REF! | therms/year
| Total commercial electricity savings by 2030= |  | #REF! | kwh/year
| Total natural gas savings by 2030= |  | #REF! | therms/year
2. GHG Calculations: | Total Emissions Savings (MT)= (Se/1000×Efa)+(Sg/10 × Efb/1000)
| Se = | total electricity savings (kWh)
| Sg= | total natural gas savings (therms)
| 1000 | = conversion factor for kWh to MWh (electricity equation) or from kg to metric tons (natural gas equation)
| 10 | = conversion factor for therm to MMBtu
| Total GHG Emissions Savings by 2020= |  | #REF! | metric tons CO2
| Total GHG Emissions Savings by 2030= |  | #REF! | metric tons CO2
Key Assumptions for Cost Calculations
Description |  |  | # | Unit | Equation Variable
Average hourly rate for City employees |  |  | #REF!
Average annual salary for City employees |  |  | #REF!
Up-front FTE |  |  | 0.25
Up-front Capital Cost |  |  | 10000
Data Sources for Cost Calculations
3. Cost Calculations: | Total Cost $= (Investment cost) - (cost savings)
| Total Cost by 2020= | #REF!
Total Cost by 2035=

## W.1.1
Strategy W.1.1 - Monitoring Worksheet
2013-12-05 | = lastest update
Strategy Name | Reduce Community Water Consumption by 20%
Emissions Category | Water
Strategy Description | Community Water Consumption. Meet State water use reduction requirements, under the Water Conservation Act of 2009 (SB7x7), to reduce water consumption by 20 % from the 2005 baseline.
Key Implementing Actions | Status | Target date | Implementing Action
| Not Started | 2014 | Action W-1.1a: Increase the efficiency of existing community plumbing fixtures and promoting available rebates from utility companies for the installation of higher efficiency plumbing fixtures.
| Not Started | 2014 | Action W-1.1b: Prepare and adopt a Water Efficient Landscaping Ordinance.
Key Assumptions for Resource Savings and GHG Calculations
Description |  |  | # | Unit | Equation Variable | Notes:
Total GHG Emissions (MT CO2e) of Water in 2005 |  |  | 443.1952 | MT CO2e | T
Percent Reduction in Water Consumption, relative to 2005 |  |  | 0% | % | Z | CAP Target = 20% per capita reduction in water consumption by 2020.
GHG Savings: | Reduce Community Water Consumption: Total GHG Savings = T x Z
| Total GHG Savings by 2020 = |  | 0 | metric tons CO2